## Slide 1
Regional Competitiveness Operational Programme in Croatia – Economic aspect
25 March 2014

## Slide 2: RCOP - allocation
Year | Total IPA/ERDF allocation (EUR, EU contribution)
2007 | 11.050.250
2008 | 11.503,323
2009 | 10.092,382
2010 | 14.200.000
2011 | 14.400.000
2012 | 10.348,000
2013 | 116.185,640
Total 2007 – 2013 | 187.779.594

## Slide 3: RCOP – allocation per Priority
Priority Axis | Fund | Community funding | National counterpart | Breakdown of the national counterpart |  | Total funding
 |  |  |  | National public funding | National private funding | 
 |  | (a) | (b)=(c)+(d) | (c) | (d) | (e)=(a)+(b)
Priority axis 1: Development and upgrading of the regional infrastructure and enhancement of the attractiveness of regions | ERDF | 62.163.242 | 3.500.000 | 3.5000.000 | 0 | 65.663.242
Priority axis 2: Enhancing the competitiveness of the Croatian economy | ERDF | 113.796.167 | 30.249.615 | 6.500.000 | 23.749.615 | 144.045.782
Priority axis 3: Technical Assistance | ERDF | 11.820.186 | 2.085.916 | 2.085.916 | 0 | 13.906.102
Total | ERDF | 187.779.595 | 35.835.531 | 12.085.916 | 23.749.615 | 223.615.126

## Slide 4: RCOP – allocation per Priority
Chart: 
| Priority 1 | Priroity 2 | Priority 3
Financial allocation per priority | 0.29 | 0.65 | 0.06

## Slide 5: RCOP – De-commitment
Year | Total IPA/ERDF | De-commitment
2007 | 11.050.250 | 
2008 | 11.600.000 11.503.323 | - 96.677,00
2009 | 12.699.500 10.092.382 | -2.607.118
2010 | 14.200.000 | 
2011 | 14.400.000 | Hope for the best, work in progress
2012 | 10.348,000 | 
2013 | 116.185,640 | 
Total 2007 – 2013 | 187.779.594 | 

## Slide 6: RCOP – Projects prepared (I)
Period: 01/01/2007 – 30/06/2013
Total contracts: 144
  112 grant contracts
    102 contracted
    Approx. 10 under evaluation
  20 service contracts (of which 2 single tenders)
    17 contracted
    3 under preparation (of which 2 single tenders)

## Slide 7: RCOP – Projects prepared (II)
  5 FW contracts
    All contracted
  6 supply contracts
    3 contracted
    1 under evaluation
    2 under preparation
  1 works contract
    contracted

## Slide 8: RCOP – Projects prepared (III)
144
100%
Total planned
128
88.88%
Contracted
11
7.63%
Under evaluation
5
3,47%
Under preparation

## Slide 9: RCOP – Projects prepared (IV)
79.379.595,00
100%
Total available
65.817.346,34
82.91%
Contracted
12.137.508,45
15.29%
Under evaluation
1.659.863,95
2.09%
(2007-2013/06/30)
Under preparation

## Slide 10: RCOP – 01/07/2013 - 31/12/2013
Published CfPs | IB1 | Available amount | Thresholds | Type of Call
Business-Related Infrastructure | MRDEUF | 26.950.000,00 | 1.000.000 – 10.500.000 | Open
Increasing SME’s economic activity and competitiveness | MEC | 30.300.000,00 | 500.000 – 3.500.000 | Open
Applying ICT solutions to improve business processes | MEC | 3.166.000,00 | / | Open (on-going)
Assistance in managing OP and capacity building | ME | 6.402.117,55 | Defined per each OP body | Restricted

## Slide 11: RCOP – 01/07/2013 - 31/12/2013
Published CfPs | IB1 | Available amount | Thresholds | Type of Call
Development of Research Infrastructure on University of Rijeka Campus | MSES | 23.622.687,50 | n/a | Restricted
Infrastructure Project pipeline preparation for ERDF 2014 – 2020 | MSES | 6.000.000,00 | 0 – 6.000.000,00 | Restricted
Strengthening capacities for research & development & innovation | MSES | 11.311.839,45 | 200.000,00 – 1.000.000,00 | Open

## Slide 12: Challenges
Avoiding risk of decommitment
Timely contracting to allow better absorption
Implementing grant schemes – allocated vs contracted vs spent funds (increases risk of de-commitment)
Timely and continuous guidance to contractors and grant beneficiaries
Recoveries

## Slide 13: Positive impact (I)
Positive impact very difficult to assess at the level of the Programme in terms of its overall results;
A great number of project still under implementation and evaluation
Only achievements of outputs and specific project results available for analysis (some projects more successful and focused than others)

## Slide 14: Positive impact (II)
Increased capacities within business sector; however more investments required (grants)
Increased capacities of grant beneficiaries to implement grant schemes
Inreased capacities of Operating structure in implementation of Ops – procedures for continuation of operation in place

## Slide 15: Positive impact (II)
Tourism related projects – attractive, but local character
Major Project, BIOcentre – attractive and ambitious, needs to provide results yet
Business incubators – required, but still need to attract more business

## Slide 16
Its never too early to start preparing for management and implementation of Structural funds
Big inflow of funds that needs to be awarded in a way to produce results and spent in line regulation
Understanding:
Strategies – EU and national
Legal context
Processes and procedures
Lessons learned

## Slide 17
All good practices (PRAG) and lessons learned should be used to prepare a good legal framework for awarding grants
Managing projects under SI requires good understanding of differences – during duration of one single contract two different legal frameworks are in place (imposing certain rules)
Lessons learned

## Slide 18
New structures require new Manuals – previous knowledge and practice very important (however, sometimes it hinders from seeing requirements from different perspective)
Staff retention is crucual
Additional staff required – „old” staff become mentors (additional workload)
Lessons learned

## Slide 19
National legislation instead of PRAG
  Takes time to adapat (on the level of insitution, segregation)
  Takes time to learn
New complex legislation – bigger investments – State Aid – Revenues – Durability
Lessons learned

## Slide 20: Lessons learned
Sharing:
Information Trainings
Knowledge Meetings, Networks
Lessons learned Important messages
Good practice Manulas
At the level of office, department, institution, operational structure, public events, other countries

## Slide 21: Questions?

## Slide 22: Thank you for your attention!
Andrijana Anić-Antić,
CFCA, Croatia
Andrijana.AnicAntic@safu.hr